## Sheet1
Phase/Tasks | Delivrable/ Documents Produced | Who Assigned | Initial Due Date | Final Due Date | Date Completed
Incepton
Hold Initial Project Meeting | Agenda | Team Spannabe | 2009-10-01 | 2009-10-01 | 2009-10-01
Produce Minutes | Minutes | Spencer Border | Every Week | Every Week | Every Week
Produce Project Plan | Project Plan | Spencer Border | Every Week | Every Week | Every Week
Hold Initial Customer Meeting | Agenda | Team Spannabe | 2009-09-30 | 2009-09-30 | 2009-09-30
Team Website | Website | Anthony Marley | 2009-10-06 | 2009-10-06 | 2009-10-06
Elaboration
Construct Use Case Diagram | Use Case Diagram | Benjamin Fagin
Create initial list of functional requirements | Functional Requirements | Team Spannabe | 2009-10-16 | 2009-10-20 | 2009-10-20
Formalize functional requirements | Functional Requirements | Nathan Folkert | 2009-10-18 | 2009-10-20 | 2009-10-20
SRS Appendix A - DD actor descriptions | Actor Descriptions | Spencer Border | 2009-10-18 | 2009-10-20 | 2009-10-20
SRS Section V class diagrams | Class Diagrams | Anthony Marley | 2009-10-18 | 2009-10-20 | 2009-10-20
SRS Appendix A class description | Class Description | Benjamin Fagin | 2009-10-18 | 2009-10-20 | 2009-10-20
SRS Section III and IV | SRS III and IV | Nathan Folkert | 2009-10-18 | 2009-10-20 | 2009-10-20
SRS Section I and II | SRS I and II | Nathan Folkert, Anthony Marley | 2009-10-27 | 2009-10-27 | 2009-10-27
SRS Appendix A attribute descriptions | Attribute Descriptions | Benjamin Fagin | 2009-10-27 | 2009-10-27 | 2009-10-27
SRS Appendix B - Raw use case point analysis | Use case point analysis | Spencer Border, Anthony Marley | 2009-10-27 | 2009-10-27 | 2009-10-27
SRS Appendix E - Screens and Reports List | Screens and Reports List | Nathan Folkert | 2009-10-27 | 2009-10-27 | 2009-10-27
Use Case Assignments
Member | Use Case | UCP Value | # of Screens
Nathan Folkert | Modify Unpublished Entry | 10 | 1
Spencer Border | Upload Additional Data | 10 | 1
Nathan Folkert | Modify Published Entry | 5 | 0
Nathan Folkert | Manage Contributor Accounts | 5 | 1
Spencer Border | Create Entry | 5 | 1
Anthony Marley | Login | 5 | 5
Spencer Border | Publish Entry | 5 | 1
Anthony Marley | Search | 10 | 1
Ben Fagin | Find Similar Entries | 10 | 0
Nathan Folkert | Browse by Tree | 10 | 0
Anthony Marley | Retrieve Citation | 5 | 1
Ben Fagin | View Published Entries | 5 | 1
Ben Fagin | Create Collection | 5 | 1
Spencer Border | Modify Collection | 5 | 1